| Western Student Connections Work Placement Coordination: General Process 2010 NB: This process may be adjusted for individual schools based on local needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | School/TAFE responsibility |  |  | WSC responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  |  | Term 4 |  |  |  | Term 1 |  |  | Term 2 |  |  | Term 3 |  |  | Term 4 |  |  |
| Preliminary Stage |  |  | Oct |  | Nov | Dec | Feb | Mar | Apr | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| Update employer database |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact schools/TAFE for calendar dates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare draft calendar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Publish draft calendar/adjusted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Stage 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SWL Calendar finalised and published |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| School/TAFE VET Induction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WSC processes explained to students |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student Registration Forms completed by Year 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student information entered on Pathways |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employer lists to VET/TVET teachers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Placement Request Forms completed by students/teacher |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Placement Request Forms forwarded to WSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Stage 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work Readiness Sessions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WSC presentation at VET Network meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Stage 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| New employers receive Employer Pack & complete Employer Registration form |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Students’ first SWL placements organised/conducted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Students receive Student Pack |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Schools/TAFE receive Placement summaries, SPRs etc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SWL arrangements confirmed with schools/TAFE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Stage 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WSC phones employer on first day of placements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| VET teacher contacts employer during placements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employer completes evaluation form and returns it to WSC / copy to school/TAFE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Post placement follow-up with student |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Certificate of Appreciation to employers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Students’ Second Placements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student Registration Forms completed for Year 12 placement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Students details updated on Pathways |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employer lists to schools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Placement Request Forms completed & forwarded to WSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Placements organised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Second placement: Students’ second placements are organised for Term 4 or Term 1 and follow the same process as for their first placement.

SWL Calendar: Calendar is updated and/or adjusted throughout the year as required.

Placement Request Form: Only students to be placed for a particular block should be included. i.e. Those work-ready.